## Gantt Chart
GANTT CHART
PROJECT TITLE |  | ROZAAX
PROJECT COORDINATOR |  | Lidia Arenillas | FECHA | [6 empty] | 2024-03-01
| TASK |  | PHASE ONE | [5 empty] | PHASE TWO | [11 empty] | PHASE THREE
|  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22
0 | Coordination of the Project
1 | PHASE 1: application of the CLIMAAX common methodology
1.1 | Kick-off meeting Phase 1 | bar: M1
1.2 | Definition of scope and objectives | bar: M1 to M6
1.3 | Application CLIMAAX Toolbox | bar: M1 to M6
1.4 | Weekly meeting follow-up | bar: M1 to M6
1.5 | Collaboration with University | bar: M3 to M6
1.6 | Deliverable 1 | bar: M5 to M6
2 | PHASE 2: refined regional/local high-resolution analysis and risk assessment
2024-01-02 | Kick-off-meeting Phase 2 | bar: M7
2024-02-02 | Intgeration local dataset in CLIMAAX | bar: M8 to M18
2024-03-02 | Weekly meeting follow-up | bar: M8 to M18
2024-04-02 | Collaboration with University | bar: M7 to M18
2024-06-02 | Deliverable 2 | bar: M15 to M18
3 | PHASE 3: Exploration of local adaptation strategies and improved risk management plans
2018-01-03 | Kick-off-meeting Phase 3 | bar: M19 to M22
2018-02-03 | Design Adaptation Climate Plan | bar: M20 to M22
3.3 | Participative multiactor meetings | bar: M20 to M22
3.4 | Scientific publications and activities | bar: M19 to M22
3.5 | Deliverable 3 | bar: M19 to M22
4 | Communication Plan